## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
No | Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
1 | Login | Authentication | Simple | Iteration 1 | SE151446 | Bùi Khôi Nguyên
2 | Forget Password | Authentication | Simple | Iteration 1 | SE151446 | Bùi Khôi Nguyên
3 | Register | Authentication | Simple | Iteration 1 | SE151446 | Bùi Khôi Nguyên
4 | View Profile | Authentication | Simple | Iteration 1 | SE151446 | Bùi Khôi Nguyên
5 | Edit Profile | Authentication | Simple | Iteration 1 | SE151446 | Bùi Khôi Nguyên
6 | View list of Room( search , sort , ..) | Manage Rooms | Complex | Iteration 1 | SE151488 | Hoàng Minh Thuận
7 | Add room | Manage Rooms | Simple | Iteration 1 | SE151488 | Hoàng Minh Thuận
8 | Update Room | Manage Rooms | Simple | Iteration 1 | SE151488 | Hoàng Minh Thuận
9 | Delete room | Manage Rooms | Simple | Iteration 1 | SE151488 | Hoàng Minh Thuận
10 | View list of customers ( search , sort ) | Manage Customers | Complex | Iteration 1 | SE151436 | Trần Thiên Phúc
11 | Update customer | Manage Customers | Simple | Iteration 1 | SE151436 | Trần Thiên Phúc
12 | Add customer | Manage Customers | Simple | Iteration 1 | SE151436 | Trần Thiên Phúc
13 | Delete customer | Manage Customers | Simple | Iteration 1 | SE151436 | Trần Thiên Phúc
14 | View list of staff ( search , sort ,.. ) | Manage Staff | Complex | Iteration 1 | SE150445 | Phạm Hưng Phát
15 | Update staff | Manage Staff | Simple | Iteration 1 | SE150445 | Phạm Hưng Phát
16 | Add staff | Manage Staff | Simple | Iteration 1 | SE150445 | Phạm Hưng Phát
17 | Delete staff | Manage Staff | Simple | Iteration 1 | SE150445 | Phạm Hưng Phát
18 | Send Feedback | Manage Feedback | Simple | Iteration 1 | SE151447 | Nguyễn Hoàng Hải
19 | View Feedback (search , sort ,…) | Manage Feedback | Complex | Iteration 1 | SE151447 | Nguyễn Hoàng Hải
20 | View list of bill ( search , sort ,..) | Manage Bill | Complex | Iteration 2 | SE151446 | Bùi Khôi Nguyên
21 | Update bill | Manage Bill | Simple | Iteration 2 | SE151446 | Bùi Khôi Nguyên
22 | View Revenue | Manage Revenue | Simple | Iteration 2 | SE151488 | Hoàng Minh Thuận
23 | Compute Revenue Statistic | Manage Revenue | Simple | Iteration 2 | SE151488 | Hoàng Minh Thuận
24 | View Regulation | Manage Regulation | Simple | Iteration 2 | SE151436 | Trần Thiên Phúc
25 | Create Regulation | Manage Regulation | Simple | Iteration 2 | SE151436 | Trần Thiên Phúc
26 | Update Regulation | Manage Regulation | Simple | Iteration 2 | SE151436 | Trần Thiên Phúc
27 | Delete Regulation | Manage Regulation | Simple | Iteration 2 | SE151436 | Trần Thiên Phúc
28 | View Notification | Manage Notification | Simple | Iteration 2 | SE150445 | Phạm Hưng Phát
29 | Add Notification | Manage Notification | Simple | Iteration 2 | SE150445 | Phạm Hưng Phát
30 | Delete Notification | Manage Notification | Simple | Iteration 2 | SE150445 | Phạm Hưng Phát
31 | Update Notification | Manage Notification | Simple | Iteration 2 | SE150445 | Phạm Hưng Phát
32 | View Contract | Manage Booking | Simple | Iteration 2 | SE151447 | Nguyễn Hoàng Hải
33 | Add Contract | Manage Booking | Simple | Iteration 2 | SE151447 | Nguyễn Hoàng Hải
34 | Delete Contract | Manage Booking | Simple | Iteration 2 | SE151447 | Nguyễn Hoàng Hải
35 | Update Contract | Manage Booking | Simple | Iteration 2 | SE151447 | Nguyễn Hoàng Hải
36 | View Service (search , sort ) | Manage Service | Complex | Iteration 3 | SE151446 | Bùi Khôi Nguyên
37 | Add Service | Manage Service | Simple | Iteration 3 | SE151488 | Hoàng Minh Thuận
38 | Delete Service | Manage Service | Simple | Iteration 3 | SE150445 | Phạm Hưng Phát
39 | Update Service | Manage Service | Simple | Iteration 3 | SE151436 | Trần Thiên Phúc
40 | Checkout | Manage Payment | Simple | Iteration 3 | SE151447 | Nguyễn Hoàng Hải