## Week 1
PROJECT REPORT
Group | 2 : Phạm Hưng Phát(leader) - Hoàng Minh Thuận - Bùi Khôi Nguyên - Nguyễn Hoàng Hải - Trần Thiên Phúc
Week | <09/05/2022-15/05/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Share work | In Progress | Divide the project into several parts and the team leader will divide them equally among the team members
2 | Introduce | Completed | Introduce in detail the purpose and benefits of the project implementation
3 | Listed | In Progress | List functions and possible scenarios for innkeepers and customers
4 | SRS | In Progress | SRS diagram design
5 | Screen flow | In Progress | This part shows the system screens and the relationship among screens.
6 | Database | In Progress | Design database for application
7 | Code | In Progress | Implement code, start dividing next week
8 | Product backlog | In Progress | Distributing work to team members
9 | ERD | In Progress | Database design for ERD application
10 | Context diagram | In Progress | Need a redesign
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Division of work | Phạm Hưng Phát | Need to divide the work more specifically to save time
2 | Product introduction | Phạm Hưng Phát, Hoàng Minh Thuận | Words need to be changed to fit the context
3 | Working with SRS of Project Hostel Management | Phạm Hưng Phát, Nguyễn Hoàng Hải | In progress
4 | Design the necessary screens of the application | Bùi Khôi Nguyên and Trần Thiên Phúc | In progress
5 | List all the function | All members | In progress
6 | Design database | All members | In progress
7 | Implement code | All members | Need to complete the quests first
8 | Write Product Backlog | Hoàng Minh Thuận, Phạm Hưng Phát | Need to finish next week
9 | Database design for ERD application | Bùi Khôi Nguyên, Trần Thiên Phúc | In progress
10 | Write down Context Diagram | Nguyễn Hoàng Hải, Phạm Hưng Phát | In progress
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Members meeting on time, resulting in delayed project progress | In Progress | The team leader needs to make stricter rules for the members to follow
2 | No clear division of work | In Progress | The team leader needs to learn about the tasks to distribute them more evenly
3 | Lack of understanding of the language makes the introduction not express the context and details of the application | In Progress | Need to refer to some more sample documents online and all members have to give their opinions
4 | Wrong database design and SRS | In Progress | Need to review the relationships of each table
5 | The design lacks some necessary screens | In Progress | Thuan will add later
6 | Code has not been implemented yet due to unresolved related issues | Pending | Complete all the tasks to start implement code
7 | Missing some components of the context diagram | In Progress
8
9
10
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Database | 2022-05-27 | Database building
2 | Implement code | Pending | Add key functions to the software
3 | Testing | Pending | Test possible error cases and fix them
4 | Add necessary functions for innkeepers and users | 2022-05-27 | Update new features that users need to be able to manipulate more easily with the application
5 | Complete Context Diagram | 2022-05-27
6 | Complete SRS | 2022-05-27
7 | Comple Product Backlog | 2022-05-27
8
9
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C31: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 2
PROJECT REPORT
Group | 2 : Phạm Hưng Phát(leader) - Hoàng Minh Thuận - Bùi Khôi Nguyên - Nguyễn Hoàng Hải - Trần Thiên Phúc
Week | <16/05/2022-22/05/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Listed | Completed | List functions and possible scenarios for innkeepers and customers
2 | SRS | Completed | SRS diagram design
3 | Screen flow | Completed | This part shows the system screens and the relationship among screens.
4 | Database | In Progress | Design database for application
5 | Code | Pending | Implement code, start dividing next week
6 | Product backlog | In Progress | Distributing work to team members
7 | ERD | In Progress | Database design for ERD application
8 | Context diagram | Completed | A schema is used to provide an overview of the entire system.
9 | Design layout | In Progress | Design layoutwith CSS, bootstrap, JS
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Product introduction | Phạm Hưng Phát, Hoàng Minh Thuận | Completed
2 | Working with SRS of Project Hostel Management | Phạm Hưng Phát, Nguyễn Hoàng Hải | Completed
3 | Design the necessary screens of the application | Bùi Khôi Nguyên, Trần Thiên Phúc | Completed
4 | List all the function | All members | Completed
5 | Design database | All members | In Progress
6 | Implement code | All members | Pending
7 | Write Product Backlog | Hoàng Minh Thuận, Phạm Hưng Phát | In Progress
8 | Database design for ERD application | Bùi Khôi Nguyên, Trần Thiên Phúc | Completed
9 | Write down Context Diagram | Nguyễn Hoàng Hải, Phạm Hưng Phát | Completed
10 | Layout | Bùi Khôi Nguyên, Trần Thiên Phúc | In Progress
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Members meeting on time, resulting in delayed project progress | In Progress | The team leader needs to make stricter rules for the members to follow
2 | No clear division of work | In Progress | The team leader needs to learn about the tasks to distribute them more evenly
4 | Wrong database design and SRS | Pending | Need to review the relationships of each table
5 | The design lacks some necessary screens | Completed | Solved
6 | Code has not been implemented yet due to unresolved related issues | In Progress | Complete all the tasks to start implement code
7 | Missing some components of the context diagram | In Progress | Group discussion to find a solution
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Database | 27/05/2022 | Database building
2 | Implement code | Pending | Add key functions to the software
3 | Testing | Pending | Test possible error cases and fix them
4 | Completing the product backlog | 27/05/2022 | Let everyone follow and do their own thing
5 | Completing the layout | 27/05/2022 | Tran Thien Phuc and Bui Khoi Nguyen
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 |  |  | 0
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C31: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 3
PROJECT REPORT
Group | 2 : Phạm Hưng Phát(leader) - Hoàng Minh Thuận - Bùi Khôi Nguyên - Nguyễn Hoàng Hải - Trần Thiên Phúc
Week | <23/05/2022-29/05/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS | In Progress | Finalize the document
2 | Screen | In Progress | Complete the necessary screen of the project
3 | Implement code | In Progress | Coding
4 | Database | In Progress | Design database for application | x
5 | Code | Pending | Implement code, start dividing next week | x
6 | Product backlog | In Progress | Distributing work to team members | x
7 | ERD | In Progress | Database design for ERD application | x
8 | Weekly report | Completed | Statistics of the group's work
9 | Design layout | In Progress | Design layoutwith CSS, bootstrap, JS | x
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Group meeting | All members | Meeting on gg meet at 8pm on Tuesday 3rd and 7th to discuss the completion of the database, division of functions, completion of the layout
2 | Group meeting | All members | Meeting on gg meet at 8pm on Monday to discuss about the screen
3 | Group meeting | All members | Meeting on gg meet at Friday to discuss about the code and layout
4 | Iteration | Phạm Hưng Phát | Divide the iterations for each person to be reasonable
5 | Design database | All members | Completed on Thursday | x
6 | Implement code | All members | Iteration 1 : Nguyên (Authentication) , Thuận (Manage room), Phát(Manage Staff), Phúc(Manage Customer), Hải(Manage Feedback) | x
7 | Write Product Backlog | Hoàng Minh Thuận, Phạm Hưng Phát | In Progress | x
10 | Layout | Bùi Khôi Nguyên, Trần Thiên Phúc | Layout redesign | x
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Members meeting on time, resulting in delayed project progress | In Progress | The team leader needs to make stricter rules for the members to follow
2 | No clear division of work | In Progress | The team leader needs to learn about the tasks to distribute them more evenly
4 | Wrong database design and SRS | In Progress | Need to review the relationships of each table
5 | The design lacks some necessary screens | Completed | Solved
6 | Code has not been implemented yet due to unresolved related issues | Completed | Complete all the tasks to start implement code
7 | Missing some components of the context diagram | Completed | Group discussion to find a solution
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Database | 2022-04-06 | Database building
2 | Implement code | Pending | Add key functions to the software
3 | Testing | Pending | Test possible error cases and fix them
4 | Completing the product backlog | 2022-04-06 | Let everyone follow and do their own thing
5 | Completing the layout | 2022-04-06 | Tran Thien Phuc and Bui Khoi Nguyen
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 |  |  | 0
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C28: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 4
PROJECT REPORT
Group | 2 : Phạm Hưng Phát(leader) - Hoàng Minh Thuận - Bùi Khôi Nguyên - Nguyễn Hoàng Hải - Trần Thiên Phúc
Week | <30/05/2022-05/06/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS | In Progress | Finalize the document
2 | Screen | In Progress | Complete the necessary screen of the project
3 | Implement code | In Progress | Coding
4 | Database | In Progress | Design database for application
5 | Code | Pending | Implement code, start dividing next week
6 | Product backlog | In Progress | Distributing work to team members
7 | ERD | In Progress | Database design for ERD application
8 | Weekly report | Completed | Statistics of the group's work
9 | Design layout | In Progress | Design layoutwith CSS, bootstrap, JS
10 | Iteration 1 | In Progress | Authentication, Manage room, Manage Staff,Manage Customer,Manage Feedback
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Group meeting | All members | Meeting on gg meet at 8pm on Tuesday 3rd and 7th to discuss the completion of the database, division of functions, completion of the layout
2 | Group meeting | All members | Meeting on gg meet at 8pm on Monday to discuss about the screen
3 | Group meeting | All members | Meeting on gg meet at Friday to discuss about the code and layout
4 | Iteration | Phạm Hưng Phát | Divide the iterations for each person to be reasonable
5 | Design database | All members | Completed on Thursday
6 | Implement code | All members | Iteration 1 : Nguyên (Authentication) , Thuận (Manage room), Phát(Manage Staff), Phúc(Manage Customer), Hải(Manage Feedback)
7 | Write Product Backlog | Hoàng Minh Thuận, Phạm Hưng Phát | In Progress
10 | Layout | Bùi Khôi Nguyên, Trần Thiên Phúc | Layout redesign
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Members meeting on time, resulting in delayed project progress | In Progress | The team leader needs to make stricter rules for the members to follow
2 | No clear division of work | In Progress | The team leader needs to learn about the tasks to distribute them more evenly
4 | Wrong database design and SRS | In Progress | Need to review the relationships of each table
5 | The design lacks some necessary screens | Completed | Solved
6 | Code has not been implemented yet due to unresolved related issues | Completed | Complete all the tasks to start implement code
7 | Missing some components of the context diagram | Completed | Group discussion to find a solution
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Database | 2022-06-12 | Database building
2 | Implement code | In Progress | Add key functions to the software
3 | Testing | Pending | Test possible error cases and fix them
4 | Completing the product backlog | 2022-06-12 | Let everyone follow and do their own thing
5 | Completing the layout | 2022-06-12 | Tran Thien Phuc and Bui Khoi Nguyen
6 | Iteration 1 | 2022-06-15 | Complete the Iteration 1
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 |  |  | 0
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C29: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 5
PROJECT REPORT
Group | 2 : Phạm Hưng Phát(leader) - Hoàng Minh Thuận - Bùi Khôi Nguyên - Nguyễn Hoàng Hải - Trần Thiên Phúc
Week | <06/06/2022-12/06/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS | Completed | Finalize the document
2 | Screen | Completed | Complete the necessary screen of the project
3 | Implement code | In Progress | Coding
4 | Database | Completed | Design database for application
5 | Code | In Progress | Implement code
6 | Product backlog | Completed | Distributing work to team members
7 | ERD | Completed | Database design for ERD application
8 | Weekly report | Completed | Statistics of the group's work
9 | Design layout | Completed | Design layoutwith CSS, bootstrap, JS
10 | Iteration 1 | In Progress | Authentication, Manage room, Manage Staff,Manage Customer,Manage Feedback
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Group meeting | All members | Meeting on gg meet at 8pm on Tuesday 3rd and 7th to discuss the completion of the database, division of functions, completion of the layout
2 | Group meeting | All members | Meeting on gg meet at 8pm on Monday to discuss about the screen
3 | Group meeting | All members | Meeting on gg meet at Friday to discuss about the code and layout
4 | Iteration 2 | Phạm Hưng Phát | Divide the iteration 2 for each person to be reasonable
5 | Design database | Hoàng Minh Thuận, Phạm Hưng Phát | Redesigning the Customer table
6 | Implement code: complete Iteration 1 to make next part | All members | Iteration 1 : Nguyên (Authentication) , Thuận (Manage room), Phát(Manage Staff), Phúc(Manage Customer), Hải(Manage Feedback)
7 | Write Product Backlog | Hoàng Minh Thuận, Phạm Hưng Phát | Completed
8 | Add template | Bùi Khôi Nguyên, Trần Thiên Phúc | Inprogress
9 | Validate | All members | Inprogress
10 | Layout | Bùi Khôi Nguyên, Trần Thiên Phúc | Completed
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Members meeting on time, resulting in delayed project progress | In Progress | The team leader needs to make stricter rules for the members to follow
2 | No clear division of work | In Progress | The team leader needs to learn about the tasks to distribute them more evenly
4 | Wrong database design and SRS | Completed | Need to review the relationships of each table
5 | The design lacks some necessary screens | Completed | Solved
6 | Wrong code about Booking | In Progress | Thuan is fixing, add more fuction and screens
7 | Wrong code about Search Feedback | In Progress | Hai is fixing
8 | Wrong code about Authentication, wrong login | In Progress | Nguyen is fixing
9 | Missing some components of the context diagram | In Progress | Group discussion to find a solution
10 | Correct the date input format | In Progress | Nguyen is fixing
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Complete Authentication | 2022-06-20
2 | Implement code | In Progress | Add key functions to the software
3 | Testing | In Progress | Test possible error cases and fix them
4 | Complete fixing Manage Feedback | 2022-06-20 | Hai must finish by Monday
5 | Complete fixing Manage Room | 2022-06-20 | Thuan must finish by Wednesday
6 | Complete Manage Staff | 2022-06-20 | Phat must finish by Wednesday
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 |  |  | 0
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C31: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 6
PROJECT REPORT
Group | 2 : Phạm Hưng Phát(leader) - Hoàng Minh Thuận - Bùi Khôi Nguyên - Nguyễn Hoàng Hải - Trần Thiên Phúc
Week | <13/06/2022-19/06/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS | Completed | Finalize the document
2 | Screen | Completed | Complete the necessary screen of the project
3 | Implement code | In Progress | Coding
4 | Database | Completed | Design database for application
5 | Code | In Progress | Implement code
6 | Product backlog | Completed | Distributing work to team members
7 | ERD | Completed | Database design for ERD application
8 | Weekly report | Completed | Statistics of the group's work
9 | Design layout | Completed | Design layoutwith CSS, bootstrap, JS
10 | Iteration 1 | Completed | Authentication, Manage room, Manage Staff,Manage Customer,Manage Feedback
11 | Iteration 2 | In Progress | Start coding iteration 2
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Group meeting | All members | Meeting on gg meet at 8pm on Tuesday 3rd and 7th to discuss the completion of the database, division of functions, completion of the layout
2 | Group meeting | All members | Meeting on gg meet at 8pm on Monday to discuss about the screen
3 | Group meeting | Hoàng Minh Thuận, Phạm Hưng Phát | Meeting on gg meet at Friday to discuss about the code and layout
4 | Group meeting to make sure to complete Iteration 1 | All members | Group meeting in the classroom
5 | Iteration 2 | All members | Manage Bill (Nguyen), Manage Revenue(Thuan), Manage Regulation(Phuc), Manage Contract(Hai), Manage Notification(Phat)
6 | Design database | Bùi Khôi Nguyên, Trần Thiên Phúc, Nguyễn Hoàng Hải | Redesigning the table of Iteration 2
7 | Write Product Backlog | Hoàng Minh Thuận, Phạm Hưng Phát | Completed
8 | Add template | Bùi Khôi Nguyên, Trần Thiên Phúc | Inprogress
9 | Validate | All members | Inprogress
10 | Layout | Bùi Khôi Nguyên, Trần Thiên Phúc | Completed
11 | Code execution on how to pay | In Progress | Nguyen
12 | Revenue statistics | In Progress | Thuan
13 | Make a table of rules for the hostel | In Progress | Phuc
14 | Set up a contract between the user and the hosteler | In Progress | Hai
15 | Implement the code about the notification | In Progress | Phat
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Members meeting on time, resulting in delayed project progress | Completed | The team leader needs to make stricter rules for the members to follow
2 | No clear division of work | Completed | The team leader needs to learn about the tasks to distribute them more evenly
4 | Wrong database design and SRS | Completed | Need to review the relationships of each table
5 | The design lacks some necessary screens | Completed | Nguyen is fixing
6 | Wrong code about Booking | Completed | Thuan is fixing, add more fuction and screens
7 | Wrong code about Search Feedback | Completed | Hai is fixing
8 | Wrong code about Authentication, wrong login | Completed | Nguyen is fixing
9 | Missing some components of the context diagram | Completed | Group discussion to find a solution
10 | Correct the date input format | Completed | Nguyen is fixing
11 | Need to learn more about payment methods | In Progress | All members
12 | Not yet agreed on the idea of payment | In Progress | Group discussion to find a solution
13 | Wrong database of Manage Bill | In Progress | Nguyen is fixing
14 | The validation has not been completed yet | In Progress | Group meeting in the classroom to find solution
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Check the member's work progress | 2022-06-25
2 | Implement code | In Progress | Add key functions to the software
3 | Testing | In Progress | Test possible error cases and fix them
4 | Complete fixing Manage Feedback | 2022-06-25 | Completed
5 | Complete fixing Manage Room | 2022-06-25 | Completed
6 | Complete Manage Staff | 2022-06-25 | Completed
7 | Check the Manage Bill | 2022-06-25 | Check work progress and help to complete it
8 | Check the Manage Revenue | 2022-06-25 | Check work progress and help to complete it
9 | Check the Manage Regulation | 2022-06-25 | Check work progress and help to complete it
10 | Check the Manage Notification | 2022-06-25 | Check work progress and help to complete it
11 | Check the Manage Contract | 2022-06-25 | Check work progress and help to complete it
12 | Check validate | 2022-06-25 | Check the validate of every members
13 | Check template | 2022-06-25 | Fixing template
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 |  |  | 0
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C37: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 7
PROJECT REPORT
Group | 2 : Phạm Hưng Phát(leader) - Hoàng Minh Thuận - Bùi Khôi Nguyên - Nguyễn Hoàng Hải - Trần Thiên Phúc
Week | <20/06/2022-26/06/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS | Completed | Finalize the document
2 | Screen | Completed | Complete the necessary screen of the project
3 | Implement code | In Progress | Coding
4 | Database | Completed | Design database for application
5 | Code | In Progress | Implement code
6 | Product backlog | Completed | Distributing work to team members
7 | ERD | Completed | Database design for ERD application
8 | Weekly report | Completed | Statistics of the group's work
9 | Design layout | Completed | Design layoutwith CSS, bootstrap, JS
10 | Iteration 1 | Completed | Authentication, Manage room, Manage Staff,Manage Customer,Manage Feedback
11 | Iteration 2 | In Progress | Start coding iteration 2
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Group meeting | All members | Meeting on gg meet at 8pm on Tuesday 3rd and 7th to discuss the completion of the database, division of functions, completion of the layout
2 | Group meeting | All members | Meeting on gg meet at 8pm on Monday to discuss about the screen
3 | Group meeting | Hoàng Minh Thuận, Phạm Hưng Phát | Meeting on gg meet at Friday to discuss about the code and layout
4 | Group meeting to make sure to complete Iteration 1 | All members | Group meeting in the classroom
5 | Iteration 2 | All members | Manage Bill (Nguyen), Manage Revenue(Thuan), Manage Regulation(Phuc), Manage Contract(Hai), Manage Notification(Phat)
6 | Design database | Bùi Khôi Nguyên, Trần Thiên Phúc, Nguyễn Hoàng Hải | Redesigning the table of Iteration 2
7 | Write Product Backlog | Hoàng Minh Thuận, Phạm Hưng Phát | Completed
8 | Add template | Bùi Khôi Nguyên, Trần Thiên Phúc | Inprogress
9 | Validate | All members | Inprogress
10 | Layout | Bùi Khôi Nguyên, Trần Thiên Phúc | Completed
11 | Code execution on how to pay | Completed | Nguyen
12 | Revenue statistics | In Progress | Thuan
13 | Make a table of rules for the hostel | In Progress | Phuc
14 | Set up a contract between the user and the hosteler | In Progress | Hai
15 | Implement the code about the notification | In Progress | Phat
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Members meeting on time, resulting in delayed project progress | Completed | The team leader needs to make stricter rules for the members to follow
2 | No clear division of work | Completed | The team leader needs to learn about the tasks to distribute them more evenly
4 | Wrong database design and SRS | Completed | Need to review the relationships of each table
5 | The design lacks some necessary screens | Completed | Nguyen is fixing
6 | Wrong code about Booking | Completed | Thuan is fixing, add more fuction and screens
7 | Wrong code about Search Feedback | Completed | Hai is fixing
8 | Wrong code about Authentication, wrong login | Completed | Nguyen is fixing
9 | Missing some components of the context diagram | Completed | Group discussion to find a solution
10 | Correct the date input format | Completed | Nguyen is fixing
11 | Need to learn more about payment methods | In Progress | All members
12 | Not yet agreed on the idea of payment | Completed | Group discussion to find a solution
13 | Wrong database of Manage Bill | In Progress | Nguyen is fixing
14 | The validation has not been completed yet | In Progress | Group meeting in the classroom to find solution
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Check the member's work progress | 2022-07-02
2 | Implement code | In Progress | Add key functions to the software
3 | Testing | In Progress | Test possible error cases and fix them
4 | Complete fixing Manage Feedback | 2022-07-02 | Completed
5 | Complete fixing Manage Room | 2022-07-02 | Completed
6 | Complete Manage Staff | 2022-07-02 | Completed
7 | Check the Manage Bill | 2022-07-02 | Check work progress and help to complete it
8 | Check the Manage Revenue | 2022-07-02 | Check work progress and help to complete it
9 | Check the Manage Regulation | 2022-07-02 | Check work progress and help to complete it
10 | Check the Manage Notification | 2022-07-02 | Check work progress and help to complete it
11 | Check the Manage Contract | 2022-07-02 | Check work progress and help to complete it
12 | Check validate | 2022-07-02 | Check the validate of every members
13 | Check template | 2022-07-02 | Fixing template
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 |  |  | 0
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C37: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 8
PROJECT REPORT
Group | 2 : Phạm Hưng Phát(leader) - Hoàng Minh Thuận - Bùi Khôi Nguyên - Nguyễn Hoàng Hải - Trần Thiên Phúc
Week | <27/06/2022-03/07/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS | Completed | Finalize the document
2 | Screen | Completed | Complete the necessary screen of the project
3 | Implement code | In Progress | Coding
4 | Database | Completed | Design database for application
5 | Code | In Progress | Implement code
6 | Product backlog | Completed | Distributing work to team members
7 | ERD | Completed | Database design for ERD application
8 | Weekly report | Completed | Statistics of the group's work
9 | Design layout | Completed | Design layoutwith CSS, bootstrap, JS
10 | Iteration 1 | Completed | Authentication, Manage room, Manage Staff,Manage Customer,Manage Feedback
11 | Iteration 2 | In Progress | Re-process the contract and payment
12 | Iteration 3 | In Progress | Start code Iteration 3
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Group meeting | All members | Meeting on gg meet at 8pm on Tuesday 3rd and 7th to discuss the completion of the database, Contract, payment and bills
2 | Group meeting | All members | Meeting on gg meet at 10pm on Monday to discuss about the Payment
3 | Group meeting | Hoàng Minh Thuận, Phạm Hưng Phát | Meeting on gg meet at Friday to discuss about the code and the Iteration 3
4 | Group meeting to make sure to complete Iteration 1 | All members | Group meeting in the classroom
5 | Iteration 2 | All members | Manage Bill (Nguyen), Manage Revenue(Thuan), Manage Regulation(Phuc), Manage Contract(Hai), Manage Notification(Phat)
6 | Design database | Bùi Khôi Nguyên, Trần Thiên Phúc, Nguyễn Hoàng Hải | Redesigning the table of Iteration 2
7 | Write Product Backlog | Hoàng Minh Thuận, Phạm Hưng Phát | Completed
8 | Add template | Bùi Khôi Nguyên, Trần Thiên Phúc | Inprogress
9 | Validate | All members | Inprogress
10 | Layout | Bùi Khôi Nguyên, Trần Thiên Phúc | Completed
11 | Code execution on how to pay | Completed | Nguyen
12 | Revenue statistics | In Progress | Thuan
13 | Make a table of rules for the hostel | In Progress | Phuc
14 | Set up a contract between the user and the hosteler | In Progress | Hai
15 | Implement the code about the notification | In Progress | Phat
16 | Iteration 3 | In Progress | Manage Service ( Thuan, Nguyen, Phuc, Phat ), Manage payment( Hai )
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Members meeting on time, resulting in delayed project progress | Completed | The team leader needs to make stricter rules for the members to follow
2 | No clear division of work | Completed | The team leader needs to learn about the tasks to distribute them more evenly
4 | Wrong database design and SRS | Completed | Need to review the relationships of each table
5 | The design lacks some necessary screens | Completed | Nguyen is fixing
6 | Wrong code about Booking | Completed | Thuan is fixing, add more fuction and screens
7 | Wrong code about Search Feedback | Completed | Hai is fixing
8 | Wrong code about Authentication, wrong login | Completed | Nguyen is fixing
9 | Missing some components of the context diagram | Completed | Group discussion to find a solution
10 | Correct the date input format | Completed | Nguyen is fixing
11 | Need to learn more about payment methods | Completed | All members
12 | Not yet agreed on the idea of payment | Completed | Group discussion to find a solution
13 | Wrong database of Manage Bill | Completed | Nguyen is fixing
14 | The validation has not been completed yet | Completed | Group meeting in the classroom to find solution
15 | Wrong about contract | In Progress | Phat is fixing
16 | Need more screen about the iteration 2 and iteration 3 | In Progress | Group meeting in the classroom to find solution
17
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Check the member's work progress | 2022-07-06
2 | Implement code | Completed | Add key functions to the software
3 | Testing | In Progress | Test possible error cases and fix them
4 | Complete fixing Manage Feedback | 2022-07-06 | Completed
5 | Complete fixing Manage Room | 2022-07-06 | Completed
6 | Complete Manage Staff | 2022-07-06 | Completed
7 | Check the Manage Bill | 2022-07-06 | Check work progress and help to complete it
8 | Check the Manage Revenue | 2022-07-06 | Check work progress and help to complete it
9 | Check the Manage Regulation | 2022-07-06 | Check work progress and help to complete it
10 | Check the Manage Notification | 2022-07-06 | Check work progress and help to complete it
11 | Check the Manage Contract | 2022-07-06 | Check work progress and help to complete it
12 | Check validate | 2022-07-06 | Check the validate of every members
13 | Check template | 2022-07-06 | Fixing template
14 | Manage Service | 2022-07-06 | Need to complete
15 | Manage Payment | 2022-07-06 | Need to complete
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 |  |  | 0
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C39: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue